## Stategic Priorities - Progress
Initiative | Leader | Team Members | Start Date | Frequency | Status | Notes | % complete
Community Impact | [6 empty] | complete
Configure our staff projects to be team-centered. | Strategy & Ops Dir | All staff | 2021 | Once | Completed |  | 90
Produce a statement of principles, an operations plan, and metrics for diversity, equity, and inclusion at MCCOY. | Executive Dir | All staff | 2021 | Once | Underway | establishing as a Board Committee; developing principles and goals
Shape and promote our brand identity as an influencer and a catalyst. | Communications Dir | Executive Dir | 2021 | Ongoing | Underway | expanding social media presence and utilizing new channels | 75
Elevate our visibility among agencies and the general public year-round. | Communications Dir | Executive Dir | 2021 | Ongoing | Underway | increasing presence at community events and participating in more community efforts | 80
Design year-round activities to stay current on youth needs and perspectives. | Learning & Prof Dev Dir | Policy & Advocacy Dir Youth Engage Dir | 2021 | Ongoing | Completed and Ongoing | Quarterly staff development days | 100
Develop a list of sources we will consult for data on youth-related trends. | Learning & Prof Dev Dir | Policy & Advocacy Dir Youth Engage Dir | 2021 | Annual | Underway | staff collecting and compiling | 75
Design staff learning activities that will equip us to advocate well as a team. | Learning & Prof Dev Dir | Policy & Advocacy Dir Youth Engage Dir | 2021 | Annual | Completed and Ongoing | statehouse visits | 100
Design staff learning activities to inform our capacity-building content. | Learning & Prof Dev Dir | Policy & Advocacy Dir Youth Engage Dir | 2021 | Annual | Completed and Ongoing | regular staff discussions | 65
Board and Resource Development
Guide new and young board members into board conversations. |  | Executive Governance Chair or Vice Chair | 2021 | Ongoing | Ongoing | Orientation completed, Chair connects regularly with board members, checks in with new board members | 100
Design and conduct resource development training. |  | Resource Dev Marketing & Comm | 2021 | Annual | Ongoing | 2021 and 2022 Completed 2023 in progress | 50
Shape and inform our roles as public advocates for MCCOY. |  | Public Policy | 2021 | Ongoing | Ongoing | Committee and staff strengthening this in 2023 | 75
Build our board’s awareness of youth development issues and trends. |  | Program | 2022 | Ongoing | Started | Adding to ongoing board ed effort at board meetings, next up "IPS Update" in April '23 | 50
Update board and committee structure, roles, and communication materials. |  | Executive Executive Dir | 2021 (plan) 2022 (start) | Annual | Completed & Ongoing | Continue to evolve and develop communication materials | 60
Integrate future-oriented strategic thinking into our board discussions. |  | Executive Chair Executive Dir | 2022 | Ongoing | Completed & Ongoing | Regular updates on strategic plan, moved oral committee reports to verbal to make room for board ed and future-oriented convos | 75
Attract and prepare new board members. |  | Executive Governance Executive Dir | 2022 | Annual | Completed & Ongoing | Developed bd matrix to identify skill/influence gaps, Developed & executed orientation in 2022, 2023 | 80
Create talking points for board members to use as ambassadors of MCCOY. |  | Resource Dev Marketing & Comm | 2022 | Annual | Underway | Have developed What we Do flyer and CD collecting testimonials to be shared | 80
Organize and oversee resource development roles and results. |  | Resource Dev Marketing & Comm | 2022 | Ongoing | Underway | Board trainings regularly and rebuilt Resource Development Committee | 70
Succession Planning
Identify a person to guide the process and the person(s) who will select the future leader. |  | Governance | 2022 | Once | Completed |  | 100
Develop a timeline for recruiting and selecting the future leader. |  | Governance | 2022 | Once | Completed |  | 100
Write a position description and the selection criteria for the future leadership role. |  | Governance Executive Dir Talbott Talent | 2022 | Once | Underway |  | 65
Contact other organizations for advice. |  | Governance Talbott Talent | 2022 | Ongoing | Underway |  | 100
Gather resources to fund the selection process plus the compensation and resources for the future leader. |  | Executive Director Finance |  | Ongoing | Completed for selection process, will be part of planning with Talbott for new leader |  | 100
Publicize the leadership role and recruit candidates. |  | Governance Talbott Talent |  | Once | Underway |  | 40
Screen candidates and select the future leader. |  | Governance Talbott Talent |  | Once | Underway
Capture insights from our outgoing leader and define a post-transition role for him. |  | Governance Talbott Talent |  | Once | Underway |  | 65
Plan and launch publicity to inform key stakeholders and the general public about the transition. |  | Governance Talbott Talent |  | Once | Underway |  | 80
Officially start the new leader's term. |  | Governance |  | Once
Impact Measurement
Create measurement tools and track Internal Capacity - Teamwork | Strategy & Ops Dir | Executive Dir | 2023 | Ongoing | Underway |  | 65
Create measurement tools and track Internal Capacity - Youth Sensibility | Youth Engagement Dir | Strategy & Ops Dir | 2023 | Ongoing | Underway |  | 40 | staff changes in mid 2022 slowed progress but new efforts will be kicking off in summer and fall 2023
Create measurement tools and track Internal Capacity - Landscape Expertise | Learning & Prof Dev Dir | Learning & Prof Dev Dir | 2023 | Ongoing | Underway |  | 40
Create measurement tools and track Systems Impact - Connector | Strategy & Ops Dir | Learning & Prof Dev Dir | 2021 | Ongoing | Completed & Ongoing | staff collecting data | 75
Create measurement tools and track Systems Impact - Advocate | Strategy & Ops Dir | Learning & Prof Dev Dir | 2021 | Ongoing | Completed & Ongoing | staff collecting data | 75
Create measurement tools and track Systems Impact - Capacity Builder | Strategy & Ops Dir | Learning & Prof Dev Dir | 2021 | Ongoing | Completed & Ongoing | staff collecting data | 75
Create measurement tools and track Systems Impact - Gateway | Strategy & Ops Dir | Communications Dir | 2021 | Ongoing | Completed & Ongoing | staff collecting data | 75
Create measurement tools and track Board Composition, Structure & Engagement |  | Governance | 2021 | Ongoing | Completed & Ongoing | Board Matrix and fulfillment of gaps | 100
Create measurement tools for Advocacy & Public Policy impact |  | Public Policy Cmte | 2022-23 | Ongoing | Underway |  | 50
Create measurement tools for Resource Development impact |  | Resource Dev Cmte | 2022-23 | Ongoing | Underway |  | 40 | change in committee leadership and in our donor/grant management systems are completed that will help us push this forward in 2023